## Sheet1
Project name | Start Date | End date | Cost | Estimated Hour | Total Hour | Status
Neo Indian Institute (NIIHM) |  | 26.05.2018 | 20,000/- | 50hr |  | Completed.
DRC classes |  | 13.07.2018 | 9,400/- | 23.5hr | 28.40 min | Completed.
The layman |  |  | 30,000/- | 75hr |  | Done, final amends going on
World Machine |  |  | 8100/- | 20.25hr | 15.30 hr | onging,development phase
Genesis Technologies |  |  | 15,000/- | 37.5 hr |  | Ongoing, development phase
Parvez Elahi | 11.07.2018 |  | 21,700/- | 43.4 hr |  | Ongoing, development phase
Shiv kripa apperals | 11.07.2018 |  | 16,200/- | 40.4hr |  | Ongoing Devlopment phase
Rajbir Mandar Inn | 11.07.2018 |  | 22,700/- | 56.75hr |  | Ongoing layout phase
Chomical Sports | 11.07.2018 |  | 24,200/- | 60.5hr |  | Ongoing devlopment phase